DAMEMBRANE Content Migration, SEO Audit & Publishing Strategy A complete operational playbook for migrating 80–85 blogs to Shopify, SEO-optimizing existing content, and running a 15+ blog/month content engine. 80–85 Blogs to Migrate ¦ 30–40 Ready Drafts ¦ 15+ New Blogs/Month ¦ 9 Launch Products

Prepared by: Digital Marketing Team  |  Brand: DaMembrane  |  Platform: Shopify

SECTION 01 ¦ THE CONTENT SITUATION What we have, what needs doing, and why the off-topic blogs are actually an asset

## 1.1  Inventory of All Content Assets

| Content Source | Volume | Status | Priority Action |
| --- | --- | --- | --- |
| Current live website (Laravel) | 80–85 blogs | Mixed quality — needs SEO audit | Audit → Optimize → Migrate |
| Shopify dev site (existing) | 9 blogs | 3 skincare, 3 haircare, 3 bodycare | Keep as-is, optimize meta & internal links |
| Content writer ready drafts | 30–40 blogs | Various topics, different stages | Triage, brief, schedule for publishing |
| New content (ongoing) | 15+ per month | To be planned | Assign from keyword calendar |

⚡ The Opportunity With 80–85 existing blogs + 30–40 ready drafts + 15+ new per month, DaMembrane can have 130+ indexed pages within the first 60 days of launch. This is a massive head start over competitors who had to build from zero. Most D2C brands in India spend 6–12 months reaching this content volume. We already have it.

## 1.2  Understanding the Blog Mix — and Why Off-Topic is Fine

A common mistake new brands make is publishing only content that directly sells their products. This is wrong — and here's why it works against you:

- Google rewards topical breadth within a niche. A skincare brand publishing haircare and bodycare content is still clearly a beauty/wellness brand — this signals authority in the category.

- Off-topic blogs bring traffic now. Even if a haircare blog doesn't convert to a face scrub sale today, it builds brand awareness, grows your organic sessions, and improves your site's crawl frequency.

- You're building for the future. When DaMembrane launches haircare and bodycare products (which you've planned), those blogs will already be indexed, ranked, and driving traffic. You'll flip them into product-linked content instantly.

- Internal linking bridges the gap. A haircare blog can link to your anti-aging serum through a 'complete your routine' section. The user journey connects even across categories.

📌 Strategy Decision Publish ALL existing blogs — skincare, haircare, bodycare, and everything else. Do NOT hold them back. Instead, optimize each one with: (1) strong meta titles/descriptions, (2) internal links to relevant product or skincare blogs, and (3) a 'You might also like' section pointing to your 9 launch products where logical. This is exactly how BeMinimalist scaled — they published broadly, built authority, and monetized with product links.

SECTION 02 ¦ CONTENT AUDIT FRAMEWORK How to evaluate every blog before migrating it to Shopify

## 2.1  The 4-Category Audit System

Before migrating the 80–85 blogs from the live Laravel site, every single blog must be triaged into one of four categories. This audit should be done in a Google Sheet with one row per blog.

| Category | What It Means | Action | Time Needed |
| --- | --- | --- | --- |
| PUBLISH AS-IS | Well-written, 800+ words, covers the topic properly, has a clear structure | Add SEO meta, 2–3 internal links, check keyword in H1, publish | 30 min/blog |
| OPTIMIZE & PUBLISH | Good content but missing: keyword in title, meta description, internal links, or too short | Optimize on-page SEO, expand thin sections, add links, then publish | 1–2 hrs/blog |
| REWRITE & PUBLISH | Topic is good but content is poor quality, too short (<500 words), or outdated | Full rewrite with proper SEO brief. Assign to content writer | 3–4 hrs/blog |
| HOLD / MERGE | Duplicate topic, very thin (<300 words), or overlaps heavily with another blog | Merge into a stronger blog, or hold and expand later. Do not publish thin content. | Varies |

## 2.2  The SEO Audit Checklist — Per Blog

Run every blog through this checklist before publishing on Shopify. This takes 20–40 minutes per blog once you have the habit:

### A. Title & Meta

- Does the H1 contain the target keyword naturally?

- Is the meta title 50–60 characters with keyword near the front?

- Is the meta description 140–155 characters, includes keyword, and has a soft CTA?

- Does the URL slug use the keyword? (e.g., /blogs/skincare/best-spf-50-sunscreen-india)

### B. Content Quality

- Is the blog 800+ words? (1,200–2,000 is ideal for competitive topics)

- Is there a clear intro, body with H2/H3 subheadings, and a conclusion?

- Does it answer the search intent? (informational, comparison, or how-to?)

- Is the keyword used in the first 100 words, at least 1–2 H2s, and the conclusion?

- Are there any factual errors, outdated product claims, or broken references?

### C. Internal Linking

- Does the blog link to at least 2 other relevant blogs on the site?

- Does it link to 1 relevant product page where natural? (e.g., sunscreen blog → SPF 50 product page)

- Are the anchor texts descriptive and keyword-rich? (not 'click here')

### D. Images & Technical

- Do all images have descriptive ALT text with keywords?

- Are images compressed to under 150KB? (use TinyPNG or Shopify's built-in compression)

- Is there a featured image set (required for Shopify blog listing pages)?

- Are any external links set to open in a new tab and marked nofollow if commercial?

## 2.3  Audit Tracking Sheet Structure

Create a Google Sheet with these columns — one row per blog:

| Column | What to Fill In |
| --- | --- |
| Blog Title (original) | Copy from the live site |
| Target Keyword | The main keyword this blog should rank for |
| Search Volume (approx) | Check in Google Keyword Planner or Ubersuggest |
| Word Count | Current word count of the original blog |
| Quality Category | PUBLISH AS-IS / OPTIMIZE / REWRITE / HOLD |
| SEO Score (1–5) | Your subjective rating after running the checklist |
| Internal Links Added | List the 2–3 blogs/products you'll link to |
| Status | Draft / In Progress / Ready / Published |
| Published Date | Date it went live on Shopify |
| GSC Impressions (30d) | Check after 4 weeks — is it getting indexed? |

SECTION 03 ¦ BLOG MIGRATION PLAN — LARAVEL TO SHOPIFY Step-by-step workflow to move all 80–85 blogs without losing SEO value

## 3.1  Why Migration Must Be Done Carefully

When you move blogs from the live Laravel site to Shopify and eventually take the Laravel site offline, any blog URL that existed on the old site will return a 404 error — unless you set up 301 redirects. A 404 kills any SEO authority that blog had built. Here's the correct process:

🚨 Critical Rule Every blog URL that was live on the old Laravel site must have a 301 redirect pointing to its new Shopify URL. This transfers the SEO authority (PageRank, backlinks, Google trust) from the old URL to the new one. Do NOT go live on Shopify without setting these up first.

## 3.2  Migration Workflow — Step by Step

### Step 1 — Crawl & Export the Live Site

- Go to Screaming Frog (free up to 500 URLs) — enter the current live Laravel website URL

- Export all crawled URLs as a CSV — this gives you a complete list of every blog URL currently live

- Also export the Page Title, Meta Description, H1, and Word Count for each URL

- Cross-reference with your audit sheet — this becomes your migration master list

### Step 2 — Prioritize Migration Order

Don't migrate all 80–85 at once. Prioritize in this order:

- Priority 1 — Blogs directly related to your 9 launch products (sunscreen, face scrub, toner, etc.) — these go live first

- Priority 2 — High-traffic blogs (check Google Analytics on the Laravel site for top-visited pages)

- Priority 3 — Blogs the content writer can quickly optimize (PUBLISH AS-IS category)

- Priority 4 — Remaining blogs in batches of 10–15 per week

### Step 3 — Prepare Each Blog in Shopify

- Create the blog post in Shopify Admin > Online Store > Blog Posts

- Apply your optimized H1, meta title, meta description, and URL slug

- Paste the content — reformat headings as H2/H3 using Shopify's rich text editor

- Add internal links to 2–3 related blogs and 1 product page

- Upload the featured image with proper ALT text

- Add relevant tags (e.g., 'sunscreen', 'SPF', 'skincare routine') — these power Shopify's blog filtering

- Set the blog category correctly: Skincare Tips / Haircare / Bodycare (use Shopify blog sections)

- Save as DRAFT — do not publish until redirects are ready

### Step 4 — Set Up 301 Redirects on Shopify

- In Shopify Admin > Navigation > URL Redirects, add each redirect

- Format: Old URL (from Laravel site) → New Shopify URL

- Example: /blog/best-sunscreen-india → /blogs/skincare-tips/best-sunscreen-india

- For bulk redirects, use a CSV import (Shopify supports this) — saves hours of manual work

- Test every redirect using a redirect checker tool before going live

### Step 5 — Publish & Verify

- Once redirects are set, publish the blog on Shopify

- Use Google Search Console's URL Inspection Tool to request indexing for priority blogs

- After 2–3 weeks, check GSC to confirm the old URLs are no longer appearing and new Shopify URLs are indexed

- Set up a Google Alert for your brand name — watch for any press or blog mentions of the old URL that might need updating

## 3.3  Migration Timeline

| Week | Task | Volume | Owner |
| --- | --- | --- | --- |
| Week 1 | Crawl live site, export all URLs, create audit sheet, set up Shopify blog categories | Setup | SEO Executive |
| Week 1–2 | Audit all 80–85 blogs — categorize each as Publish/Optimize/Rewrite/Hold | 80–85 blogs | SEO + Writer |
| Week 2 | Migrate Priority 1 blogs (product-related). Set up all 301 redirects. | 15–20 blogs | SEO Executive |
| Week 3 | Migrate high-traffic blogs. Begin publishing. Request indexing via GSC. | 20–25 blogs | SEO Executive |
| Week 4 | Migrate remaining PUBLISH AS-IS blogs. Assign REWRITE blogs to writer. | 25–30 blogs | SEO + Writer |
| Month 2 | Rewritten blogs go live. All HOLD blogs reviewed and either expanded or discarded. | Remaining | Content Writer |

SECTION 04 ¦ INTERNAL LINKING STRATEGY How to connect off-topic blogs to your products and build a content web

## 4.1  Why Internal Linking Matters More Than Most People Think

Internal linking is one of the highest-ROI SEO activities that almost every small brand ignores. Here's what it does:

- Passes 'link equity' (PageRank) from high-traffic pages to product pages, boosting their ranking

- Keeps users on your site longer — reducing bounce rate, which is a Google ranking signal

- Helps Google understand your site structure and which pages are most important

- Bridges the gap between off-topic content and your core products

## 4.2  The Hub-and-Spoke Internal Linking Model

This is the same model used by BeMinimalist, Healthline, and every major content-driven brand. Structure your content as hubs (pillar pages) with spokes (cluster blogs) linking back to them.

| Hub (Pillar Page) | Spoke Blogs That Link To It | Product Page Linked From Hub |
| --- | --- | --- |
| The Complete Sunscreen Guide for Indian Skin | What is PA++++ rating, Chemical vs Physical SPF, Sunscreen for oily skin, How to reapply sunscreen, SPF myths debunked | SPF 50 Sunscreen product page |
| Complete Anti-Aging Skincare Routine | Best anti-aging ingredients, Peptides vs Retinol, Under eye care guide, Morning vs night routine, When to start anti-aging | Anti-Aging Serum + Under Eye Gel product pages |
| Face Cleansing 101: The Ultimate Guide | Double cleansing method, pH-balanced cleanser explained, Cleanser vs face wash, Cleansing for sensitive skin, Common cleansing mistakes | Cleanser product page |
| Exfoliation Guide: Scrubs, Acids & More | How often to exfoliate, Physical vs chemical exfoliation, Best scrubs for skin types, Post-exfoliation care, Scrub for dark spots | Face Scrub product page |
| Skincare Toners: Do You Really Need One? | Types of toners, AHA vs BHA toner, How to use toner, Toner for oily skin, Hydrating vs exfoliating toners | Face Toner product page |

## 4.3  How to Link Off-Topic Blogs to Your Products

For blogs about haircare, shampoo, bodycare, and other non-product topics, use these techniques to create natural bridges to your core skincare products:

### Technique 1 — The 'Complete Your Routine' Section

At the end of every haircare or bodycare blog, add a section like this:

Example "Great hair starts with a great overall routine. If you're working on your hair health, don't forget your skin needs the same care. Explore our guide to building a complete skincare routine, including the right cleanser, sunscreen, and anti-aging serum for your skin type." [Internal link to relevant skincare blog]

### Technique 2 — The 'Related Articles' Block

Add a formatted 'You Might Also Like' block at the end of every blog with 3 links to related content. For a shampoo blog, the related articles might be:

- How to build a complete hair + skin self-care routine (links to skincare routine blog)

- Best ingredients to look for in a face cleanser (links to cleanser blog)

- Why SPF matters even on cloudy days — India's sunscreen guide (links to sunscreen blog)

### Technique 3 — Contextual In-Content Links

Wherever a haircare blog mentions skin, face, or any skincare-adjacent topic, insert a natural contextual link:

Example "...just like you'd choose a shampoo based on your scalp type, choosing a cleanser based on your skin type is equally important. If you have oily skin, our guide on the best face cleansers for oily skin will help." [Link to cleanser blog]

## 4.4  Internal Linking Rules — Non-Negotiable

- Every new blog must link to at least 2 other existing blogs and 1 product page before publishing

- Use descriptive anchor text — not 'click here' or 'read more'. Use the target keyword of the page you're linking to

- Never link to the same page twice in one blog

- Do not add more than 5–6 internal links per blog — over-linking looks spammy

- Every product page should receive internal links from at least 5 different blogs

- Update old blogs with links to new blogs as they're published — this is a weekly task

SECTION 05 ¦ CONTENT PUBLISHING CALENDAR How to deploy 15+ blogs/month strategically with the writer's existing drafts

## 5.1  Content Triage — The 30–40 Existing Drafts

The content writer's 30–40 existing drafts are a gold mine — but they need to be triaged before scheduling. Use this classification system:

| Draft Category | What to Do With It | Timeline |
| --- | --- | --- |
| Product-related (sunscreen, face scrub, toner, cleanser, serum, under eye) | Prioritize. SEO brief, optimize, publish in Month 1. | Week 1–3 |
| Skincare general (routines, ingredients, skin types, skin concerns) | Medium priority. Add to Month 1–2 calendar. Great for building topical authority. | Month 1–2 |
| Haircare (shampoo, hair masks, hair oils, scalp care) | Publish strategically — 2–3 per month max. Add strong internal links to skincare content. | Month 1–3 (spread out) |
| Bodycare (body lotions, body scrubs, bath routines) | Same as haircare — publish 2 per month with skincare bridges. | Month 2–3 |
| Unrelated / too generic (no clear topic, very thin) | Flag for full rewrite. Add to backlog. Do not publish thin content under any circumstances. | Month 3+ |

## 5.2  Month 1 Publishing Calendar — Week by Week

Month 1 is about establishing topical authority for your 9 launch products. Every week, publish a mix of product-focused and general skincare content:

### Week 1–2 (Launch Week)

Goal: Get your core product pages supported by at least 2 blogs each on Day 1.

| Day | Blog Title | Keyword Target | Type | Links To |
| --- | --- | --- | --- | --- |
| Day 1 | The Complete SPF 50 Sunscreen Guide for Indian Skin 2025 | SPF 50 sunscreen India | Product Hub | Sunscreen product page |
| Day 3 | How to Build a 5-Step Skincare Routine for Beginners | skincare routine for beginners | General Skincare | Cleanser, Toner, Sunscreen pages |
| Day 5 | What Does PA++++ Actually Mean? India Sunscreen Rating Explained | PA++++ meaning sunscreen | Informational | Sunscreen blog + product |
| Day 7 | Under Eye Dark Circles: Causes and the Right Ingredients to Look For | under eye cream for dark circles | Product Support | Under Eye Gel product page |
| Day 10 | Face Scrub vs Exfoliating Toner: Which Does Your Skin Actually Need? | face scrub vs exfoliating toner | Comparison | Face Scrub + Toner pages |
| Day 12 | How to Choose a Face Cleanser for Your Skin Type | best face cleanser India | Product Hub | Cleanser product page |
| Day 14 | Anti-Aging Skincare: The Ingredients That Actually Work (Backed by Science) | anti aging serum ingredients | Product Support | Anti-Aging Serum page |

## 5.3  Ongoing Monthly Calendar Structure (Month 2 Onwards)

With 15+ blogs per month, here's how to allocate content across categories for maximum SEO impact:

| Content Type | Volume/Month | Purpose | Example Topics |
| --- | --- | --- | --- |
| Product-support blogs | 4–5 | Drive traffic to product pages. Support ranking for product keywords. | Best SPF for oily skin, How to use face toner, Anti-aging serum for 30s |
| Skincare education | 4–5 | Build topical authority. Target high-volume informational queries. | Niacinamide benefits, How to layer serums, Morning vs night routine |
| Ingredient deep-dives | 2–3 | Establish expert credibility. Low-competition, high-intent queries. | What is hyaluronic acid, Vitamin C vs Niacinamide, SPF filters explained |
| Comparison articles | 2 | Capture mid-funnel searchers comparing products/ingredients. | Face wash vs cleanser, SPF 30 vs 50, Physical vs chemical sunscreen |
| Haircare (existing drafts) | 2 | Bring in adjacent traffic. Bridge to skincare content. | Best shampoo for oily scalp, How to care for color-treated hair |
| Bodycare / general wellness | 1–2 | Broad audience building. Internal link to skincare hub pages. | Full body skincare routine, Best body moisturizer for dry skin |

## 5.4  The Content Brief Template

Every piece of content — whether from the existing drafts or new — must have a brief before the writer works on it. This ensures SEO-optimized output from the start, not a rewrite later.

Content Brief Template (use for every new blog) Blog Title: [Final H1 title] Target Keyword: [Primary keyword — use exactly as written in H1 and first 100 words] Secondary Keywords: [2–3 related keywords to use naturally in H2s and body] Search Intent: [Informational / Comparison / How-To / Product-Focused] Target Word Count: [Minimum 1,000 words — 1,500+ for competitive topics] Audience: [Beginner / Intermediate skincare user — assume no jargon knowledge] Key Questions to Answer: [List 3–5 questions this blog must fully answer] H2 Structure: [Outline the H2 subheadings — writer follows this structure] Internal Links Required: [Name 2–3 blogs + 1 product page to link to] CTA at End: [e.g., "Explore our SPF 50 Sunscreen" with link] Competitor References: [1–2 competitor blogs on this topic — research their structure, then do better]

SECTION 06 ¦ SHOPIFY BLOG SEO — PLATFORM-SPECIFIC SETUP Settings and configurations unique to Shopify that most brands miss

## 6.1  Shopify Blog Structure Setup

Shopify allows you to create multiple 'blogs' (think of them as blog categories). Set these up before migrating content:

| Shopify Blog Name | URL Path | What Goes Here |
| --- | --- | --- |
| Skincare Tips | /blogs/skincare-tips | All skincare, product-related, routine, and ingredient blogs |
| Haircare Guide | /blogs/haircare-guide | All haircare blogs — shampoo, scalp, hair routine content |
| Body & Wellness | /blogs/body-wellness | Bodycare blogs, lifestyle, self-care content |
| Ingredient Science | /blogs/ingredient-science | Deep-dive ingredient explainers — builds expert authority |

Why Separate Blog Sections? This creates clean URL structures, helps Google understand your content categories, and lets users browse by topic. It also means your Skincare Tips section builds its own topical authority without haircare posts diluting it.

## 6.2  Shopify SEO Configurations — One-Time Setup

### Theme & Technical

- Use a fast theme: Dawn (free), Sense (free), or Prestige (paid but worth it for DTC brands)

- Enable lazy loading for images — most modern Shopify themes do this by default

- Remove duplicate /collections and /products? variant URL parameters causing crawl waste

- Add a custom 404 page with links to popular blogs and products — don't lose that traffic

### Apps to Install (Free or Freemium)

| App | Purpose | Cost |
| --- | --- | --- |
| SEO King by Optify | Auto-generates meta tags, fixes broken links, image ALT text optimization | Free / Paid |
| TinyIMG | Bulk image compression + ALT text — critical for page speed | Free tier available |
| Schema Plus | Adds Product, Article, FAQ, BreadcrumbList schema automatically | Paid (~$14/mo — worth it) |
| Plug In SEO | Ongoing SEO audit — flags issues as they appear | Free / Paid |
| Judge.me Reviews | Adds star ratings to product pages — these appear in Google search results | Free tier |

## 6.3  Blog Post SEO Settings in Shopify

Every blog post in Shopify has these SEO fields — fill all of them, every time, no exceptions:

- SEO Title: 50–60 characters. Keyword first, then brand. Example: "SPF 50 Sunscreen for Indian Skin — DaMembrane"

- SEO Description: 140–155 characters. Include keyword naturally, end with a soft CTA. Example: "Looking for the best SPF 50 sunscreen for Indian skin? We break down PA++++ ratings, textures, and what actually works. Read now."

- URL Handle: All lowercase, hyphens only, keyword-rich. Example: best-spf-50-sunscreen-india

- Featured Image ALT Text: Describe the image with the keyword. Example: "SPF 50 sunscreen with PA++++ rating for Indian skin"

- Tags: Add 5–8 relevant tags per post. These power Shopify's internal blog navigation and are readable by Google.

- Author: Set a consistent author name — ideally a real persona (e.g., 'DaMembrane Skin Team'). This builds E-E-A-T (Experience, Expertise, Authoritativeness, Trustworthiness) signals.

SECTION 07 ¦ TRACKING, KPIS & WEEKLY REPORTING How to measure what's working and report it clearly

## 7.1  Tools Setup — Do This on Day 1

| Tool | What to Track | How Often |
| --- | --- | --- |
| Google Search Console | Impressions, clicks, average position, top queries, indexing status | Weekly |
| Google Analytics 4 | Organic sessions, bounce rate, pages/session, blog traffic, conversions | Weekly |
| Ubersuggest / Ahrefs Free | Keyword rankings, backlink count, domain authority | Monthly |
| Shopify Analytics | Blog page views, product page views from blog referrals, revenue attribution | Weekly |
| Google Looker Studio | Build a single dashboard combining GSC + GA4 data. Share with management monthly. | Monthly |

## 7.2  KPI Targets — Blog & Content Metrics

| KPI | Month 1 | Month 2 | Month 3 | Month 6 |
| --- | --- | --- | --- | --- |
| Total blogs published (Shopify) | 25–35 | 50–60 | 70–80 | 100+ |
| Organic sessions from blog | 500–1,000 | 2,000–4,000 | 6,000–10,000 | 25,000+ |
| Blog pages indexed in Google | 20+ | 50+ | 75+ | 100+ |
| Keywords ranking (any position) | 50+ | 150+ | 300+ | 600+ |
| Keywords in Top 10 Google | 3–5 | 15–25 | 40–60 | 100+ |
| Average blog session duration | > 1:30 min | > 2:00 min | > 2:30 min | > 3:00 min |
| Internal click-through (blog → product) | 2–3% | 4–5% | 6–8% | 10%+ |

## 7.3  Weekly SEO Workflow

This is the week-by-week operating rhythm for the SEO executive:

| Day | Task | Time |
| --- | --- | --- |
| Monday | Check GSC: any new impressions? Any crawl errors? Submit newly published URLs for indexing. | 30 min |
| Tuesday | Brief the content writer: 3–4 new blogs with full content briefs. Assign from keyword calendar. | 45 min |
| Wednesday | Review and SEO-optimize 2–3 incoming blog drafts from writer. Check internal links. | 2 hrs |
| Thursday | Publish 2–3 blogs on Shopify. Fill all SEO fields. Add featured images. Submit for indexing. | 1.5 hrs |
| Friday | Update 2–3 older blogs with new internal links to recently published content. Check any broken links. | 1 hr |
| Weekly | Update the audit tracking sheet. Note what's been published, what's in draft, what's pending rewrite. | 30 min |
| Monthly | Pull GSC + GA4 report. Track keyword rankings. Identify underperforming blogs to refresh. | 2–3 hrs |

## 7.4  What to Report to Management — Monthly

Keep management reports focused on business outcomes, not just traffic numbers. Use this structure:

- Total blogs live this month vs target

- Organic sessions this month vs last month (% growth)

- Top 5 blogs by traffic — which topics are resonating

- Keywords moved into Top 10 this month

- Blog-to-product page conversion rate (how many blog visitors clicked through to a product)

- Backlinks acquired this month (HARO mentions, guest posts, earned media)

- 3 things that worked well | 3 things to improve next month

💡 Final Note — The Compounding Effect SEO is the only marketing channel where your past work keeps paying you. Every blog you publish today will still be driving traffic 12 months from now — without any additional spend. With 80+ existing blogs, 30–40 drafts, and 15+ new blogs per month, DaMembrane is positioned to have one of the strongest content libraries in the Indian D2C skincare space within 6 months. The key is consistency and quality — never publish thin content just to hit a number. One well-optimized 1,500-word blog beats five rushed 400-word blogs every time.

— DaMembrane Digital Marketing Team